## Project Schedule
Task | Sub-Task | Period | Due Date | Status
Project Setup: Project understanding and planning | Learn basic FPGA concepts | 2 Weeks
Define project goals
Define required digital signals
FPGA Basics: FPGA environment and first designs | Install FPGA tools | 2 Weeks
Program the FPGA board
Create simple designs (LEDs, clocks)
Signal Generation Blocks: Digital signal design | Design timers and counters | 2 Weeks
Design simple control logic (FSM)
Simulate and verify signals
Platform Integration: Build the signal generation platform | Combine all hardware blocks | 2 Weeks
Connect FPGA to external hardware
Test signals on real hardware
Testing and Improvements: System testing | Generate different signal patterns | 2 Weeks
Debug timing issues
Improve ease of use
Finalization: Project completion | Final testing | 2 Weeks
Write documentation
Prepare final presentation

## Project Description
Project Description
This project focuses on building a comfortable and flexible FPGA-based platform for digital signal generation
The system will be used to generate programmable digital control signals for experimental hardware setups.
The project will mainly focus on the hardware side and FPGA design
Students will work with an FPGA development board and external lab equipment
The platform will allow easy configuration of signal timing, sequencing, and control patterns.
The goals of the project are:
1. Learn the basics of FPGA hardware and digital design
2. Gain hands-on experience with FPGA tools and lab equipment
3. Design and implement digital signal generation modules (timers, counters, control logic)
4. Build a user-friendly and configurable FPGA-based signal generation platform
5. Test, validate, and document the system using real hardware experiments

## Project Requirements
Project Requirements
Study basic FPGA concepts and digital signal generation
Get hands-on experience with an FPGA development board
Design programmable digital control signals
Implement timing, sequencing, and control logic
Build a comfortable and easy-to-use signal generation platform
Enjoy
Project specifications
FPGA development board
FPGA design software (Vivado)
Digital I/O interface (GPIO)
External hardware under test
Configurable timing and control signals
Signal monitoring tools (logic analyzer / oscilloscope)
Developement stages | Tools
Safety Lab Rules | Get a Safety Guide Tour | 1 Week
FPGA Basics | Intro material & tutorials | 2 Weeks
FPGA Tools Setup | Vivado | 1 Weeks
Basic FPGA Modules | Verilog / VHDL | 2 Week
Digital Signal Generator Design | Verilog / VHDL | 3 Week
Platform Integration | FPGA board & lab equipment | 2 Weeks
Hardware Testing & Debugging | Oscilloscope / Logic Analyzer | 2 Weeks
Final Report |  | 1 Weeks