## Chips List
Design, Fabrication & Testing Tasks for NEMO
Chip Number | Name | Content | Technology | Test/Final
1 | ANN Pathfinder | ANN TD-IMC | Tower 180 nm + Y-flash | Test chip
ANN CS-IMC
Mem array peripherals
Perliminar SIPO/PISO
Scan chain / JTAG
2 | NDC Pathfinder | NDC | Tower 180 nm + Y-flash | Test chip
Mem array peripherals
Perliminar SIPO/PISO
Scan chain / JTAG
3 | ReRAM Array |  | Tower 180 nm + ReRAM | Test chip
4 | ANN TD-IMC | ANN TD-IMC | Tower 180 nm + Y-flash | Final desgin
Write/read peripherals
PG/PWM/TDC
Controller
Scan chain / JTAG
SIPO/PISO
5 | ANN CS-IMC | ANN CS-IMC | Tower 180 nm + Y-flash | Final desgin
Write/read peripherals
DAC/ADC
Controller
Scan chain / JTAG
SIPO/PISO
6 | NDC | NDC | Tower 180 nm + Y-flash | Final desgin
Write/read peripherals
Controller
Scan chain / JTAG
SIPO/PISO
7 | ANN CS-IMC | ANN CS-IMC | Tower 180 nm + ReRAM | Optional
Write/read peripherals
DAC/ADC
Controller
Scan chain / JTAG
SIPO/PISO

## Scaling P2
NEMO Architecture Scale Up
Layer Name | Input Size | Output Size | Subarray Rows | Subarray Columns | Subarrays per PE - Columns | Subarrays per PE - Rows | Total Rows per PE | Total Columns per PE | # of ADCs per PE | Active Columns per PE | Active Rows per PE | GOPS/PE | # PEs per column | # PEs per row | Total # PEs | GOPS/Col | ADC Size X | ADC Size Y | Total PE Size X | Total PE Size Y | # of 256x256 layers | Total Size X | Total Size Y | Latency (us) | Total Throughput
1 | 256 | 256 | 8 | 8 | 8 | 1 | 8 | 64 | 8 | 8 | 8 | 10.24 | 32 | 4 | 128 | 40.96 | 55 | 200 | 440 | 200 | 4 | 7.04 | 6.4 | 102.4
1 | 256 | 256 | 8 | 8 | 8 | 2 | 16 | 64 | 8 | 8 | 8 | 10.24 | 16 | 4 | 64 | 20.48 | 55 | 200 | 440 | 200 | 4 | 7.04 | 3.2 | 204.8
1 | 32 | 32 | 8 | 8 | 8 | 2 | 16 | 64 | 8 | 8 | 8 | 10.24 | 2 | 0.5 | 1 | 2.56 | 55 | 200 | 440 | 200 | 4 | 0.88 | 0.4 | 25.6
Weight resolution | Input resolution | Latency | Layer Size
4 | 8 | 50 | 256

## Blocks
Block | Name in DB | Hierarchy | Library | Type | Chip | Technology | Owner | Effortt | Priority | Milestone | Comment
Y-flash memory array 8x8 | mem_array_yflash_8x8 | AIP | nemo_shared | Analog | ANN pathfinder | TS18PM | Dima |  | High
Y-flash memory array 32x32 | mem_array_yflash_32x32 | AIP | nemo_shared | Analog | ANN pathfinder | TS18PM | Dima |  | High
SIPO | sipo | CBB | nemo_shared | AMS | All | TS18PM | Nico |  | High |  | Yossi Shor
PISO | piso | CBB | nemo_shared | AMS | All | TS18PM | Nico |  | High
Column decoder | column_dec_5bit | CBB | nemo_shared | Digital | ANN pathfinder | TS18PM | Rishona |  | High
Row decoder | row_dec_5bit | CBB | nemo_shared | Digital | ANN pathfinder | TS18PM | Rishona |  | High
Column driver | column_driver_yflash | CBB | nemo_shared | AMS | ANN pathfinder | TS18PM | Rishona |  | High
Row driver | row_driver_yflash | CBB | nemo_shared | AMS | ANN pathfinder | TS18PM | Rishona |  | High
LVR | lvr | AIP | nemo_shared | Analog | ANN pathfinder | TS18PM | Dima |  | High
VTC | vtc | AIP | nemo_ann_tdimc | Analog | ANN pathfinder | TS18PM | Dima |  | High
Current reference | iref | AIP | nemo_shared | Analog | All | TS18PM | Dima |  | High
Charge pump | charge_pump_yflash | AIP | nemo_shared | Analog | All | TS18PM | TBD - Might get it from Tower |  | Deprioritized
JTAG/TAP/SCAN | scan | CBB | nemo_shared | Digital | All | TS18PM | TBD |  | High |  | Yossi Shor
Controller | controller | BE | nemo_shared | Digital | All | TS18PM | Nir |  | Med
Sense amplifier | sense_amp | AIP | nemo_shared | AMS | All | TS18PM | Henriette |  | Med |  | Ask Tower if they can provide IPs
Continuous time comparator | comparator_cont | AIP | nemo_ann_tdimc | AMS | ANN pathfinder | TS18PM | Dima |  | High |  | Ask Tower if they can provide IPs
TDC | tdc | CBB | nemo_ann_tdimc | AMS | ANN pathfinder | TS18PM | Dima |  | High
ADC | adc_9bit | AIP | nemo_shared | AMS | All | TS18PM | Rishona |  | High |  | Ofir / Henriette
NDC | ndc_top | TOP_CBB | nemo_ndc | AMS | NDC pathfinder | TS18PM | Mahmoud |  | High
DAC Vref | vref_dac_8bit | CBB | nemo_shared | AMS | All | TS18PM | Nir |  | Low
Clock receiver | ac_level_shifter | AIP | nemo_shared | AMS | All | TS18PM | Yousef |  | Med
Global clock | global_clock_driver | AIP | nemo_shared | AMS | All | TS18PM | Yousef |  | Med
ANN CS-IMC | ann_csimc_top | TOP_CBB | nemo_ann_csimc | AMS | ANN pathfinder | TS18PM | Rishona |  | High
ANN TD-IMC | ann_tdimc_top | TOP_CBB | nemo_ann_tdimc | AMS | ANN pathfinder | TS18PM | Dima |  | High
Y-flash + Periphery | mem_yflash_top | CBB |  |  |  |  | TBD

## DFT
Signal group | Block | Access | Purpose | Action Item | Comment
WL, BL | subarray | Analog pad | Sense or force | Define size
Vref,vtc | VTC | Analog pad | Sense or force
Vref,lvr | LVR | Analog pad | Sense or force
Vref,adc | ADC | Analog pad | Sense or force
Vref+/-dec | ADC | Analog pad | Sense or force |  | x2
Iref | VTC | Analog pad | Sense |  | Check if feasible
LVR_pbias | LVR | Analog pad | Sense
VTC_out | VTC | Digital | Sense
TDC_ref |  | Digital | Sense |  | 9 signals
Sensing componets
Current measurement (4-point probe / Kelvin structure)
ADC / Vsense |  |  |  |  | Vsense with external Vref (ramp ADC)

## Gantt
Month | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
Quarter | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  |  | Q5
Architecture | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TD-IMC ANN Y-Flash | Design start |  | TRUE | Initial math model | [5 empty] | TRUE | Math model |  |  |  | TRUE | Testchip tapeout |  |  |  | I | testing & Integration |  |  | TRUE | Final Tapeout |  |  |  | I | testing & Integration |  |  | TRUE |  | TRUE | Demo
CS-IMC ANN Y-Flash | Design start |  | TRUE | Initial math model | [5 empty] | TRUE | Math model |  |  |  | TRUE | Testchip tapeout |  |  |  | I | testing & Integration |  |  | TRUE | Final Tapeout |  |  |  | I | testing & Integration |  |  | TRUE |  | TRUE | Demo
NDC Y-Flash | Design start |  | TRUE | Initial math model | [5 empty] | TRUE | Math model |  |  |  | TRUE | Testchip tapeout |  |  |  | I | testing & Integration |  |  | TRUE | Final Tapeout |  |  |  | I | testing & Integration |  |  | TRUE |  | TRUE | Demo
Month | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01
Quarter | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4
Architecture | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
TD-IMC ANN Y-Flash | Design start |  | TRUE | Initial math model | [5 empty] | TRUE | Math model |  |  |  | TRUE | Testchip tapeout
CS-IMC ANN Y-Flash | Design start |  | TRUE | Initial math model | [5 empty] | TRUE | Math model |  |  |  | TRUE | Testchip tapeout
NDC Y-Flash | Design start |  | TRUE | Initial math model | [5 empty] | TRUE | Math model |  |  |  | TRUE | Testchip tapeout

## Gantt_detail
Month |  | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
Quarter |  | 2024-10-01: Q1; 2025-02-01: Q2; 2025-06-01: Q3; 2025-10-01: Q4; 2026-02-01: Q5
Architecture | Item | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TD-IMC ANN | Preliminary design | 2025-03-01: TRUE; 2026-05-01: I; 2026-06-01: testing & Integration; 2026-09-01: TRUE; 2026-10-01: Final Tapeout; 2027-02-01: I; 2027-03-01: testing & Integration; 2027-06-01: TRUE; 2027-08-01: TRUE; 2027-09-01: Demo
| Architecture | 2025-03-01: TRUE
| Circuit implementation | 2025-12-01: TRUE; 2026-01-01: Testchip tapeout
| Math model | 2024-12-01: TRUE; 2025-01-01: Initial math model; 2025-07-01: TRUE; 2025-08-01: Math model
CS-IMC ANN | Preliminary design | 2025-03-01: TRUE; 2026-05-01: I; 2026-06-01: testing & Integration; 2026-09-01: TRUE; 2026-10-01: Final Tapeout; 2027-02-01: I; 2027-03-01: testing & Integration; 2027-06-01: TRUE; 2027-08-01: TRUE; 2027-09-01: Demo
| Architecture | 2025-03-01: TRUE
| Circuit implementation | 2025-12-01: TRUE; 2026-01-01: Testchip tapeout
| Math model | 2024-12-01: TRUE; 2025-01-01: Initial math model; 2025-07-01: TRUE; 2025-08-01: Math model
NDC Y-Flash | Preliminary design | 2025-03-01: TRUE; 2026-05-01: I; 2026-06-01: testing & Integration; 2026-09-01: TRUE; 2026-10-01: Final Tapeout; 2027-02-01: I; 2027-03-01: testing & Integration; 2027-06-01: TRUE; 2027-08-01: TRUE; 2027-09-01: Demo
| Architecture | 2025-03-01: TRUE
| Circuit implementation | 2025-12-01: TRUE; 2026-01-01: Testchip tapeout
| Math model | 2024-12-01: TRUE; 2025-01-01: Initial math model; 2025-07-01: TRUE; 2025-08-01: Math model
Month |  | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01
Architecture | Item | 17 | 18 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
TD-IMC ANN | Architecture scaling | 2026-05-01: I; 2026-06-01: testing & Integration; 2026-10-01: TRUE; 2026-11-01: Final Tapeout; 2027-02-01: I; 2027-03-01: testing & Integration; 2027-06-01: TRUE; 2027-08-01: TRUE; 2027-09-01: Demo
Circuit implementation
Backend
Integration
CS-IMC ANN | Architecture scaling | 2026-05-01: I; 2026-06-01: testing & Integration; 2026-10-01: TRUE; 2026-11-01: Final Tapeout; 2027-02-01: I; 2027-03-01: testing & Integration; 2027-06-01: TRUE; 2027-08-01: TRUE; 2027-09-01: Demo
Circuit implementation
Backend
Integration
NDC Y-Flash | Training feasiblity | 2026-05-01: I; 2026-06-01: testing & Integration; 2026-10-01: TRUE; 2026-11-01: Final Tapeout; 2027-02-01: I; 2027-03-01: testing & Integration; 2027-06-01: TRUE; 2027-08-01: TRUE; 2027-09-01: Demo
Circuit implementation
Integration | bar: 2026-02-01 to 2026-11-01
Math model

## CS-ANN Subblocks
Subblocks | Specs | Comments
SIPO
PISO
Yflash Array
Voltage Regulator
Folded-SAR-ADC
DSA
Digital ReLU |  | Deprioritized
HV-tolerant driver
Controller
Analog 4:1 mux
OpAmps
Folded-SAR-ADC | 9-bits
OpAmp
Switches
Custom latch
DAC
PE | # instances
Column Decoder | 1
Row Decoder | 1
Column Driver | 1
Row Driver | 1
Folded-SAR-ADC | 8
Analog 4:1 mux | 8
LVR | 8
Y-flash 8x8 array | 1
Writing circuits | 8
DSA | 8

## TD-ANN_layout
Critical Blocks | Library name/Category name | Cell name | Importance (0-5) | Urgency (0-5) | Schematic status(0-5) | Shared? | Layout Effort (0-5)
Y-flash sub_array 8x8 | NEMO_dobazz/ - | yflash_array_8x8 | 5 | 5 | 5
Row/Col Decoder | ANN/NEMO | mux4:1 | 3 | 3 | 4
one hot | ANN/NEMO | one_hot | 3 | 3 | 5
pass gate (5V transistors) | ANN/NEMO | passgate_5 | 3 | 5 | 5
pass gate (1.8V transistors) | ANN/NEMO | passgate_1.8 | 3 | 5 | 5
Subarr wrapper (contains Row/Col Decoder & subarr ) | ANN/NEMO | subarray_mux_wrap | 3 | 5 | 4
Clock Generator* | ANN/NEMO | clkgen | 5 | 5 | 0
OTA* | NEMO_dobazz/ - | ota_half_wrapper | 5 | 5 | 2 |  | 4
LVR (OTA+pMOS) | ANN/NEMO | lvr | 5 | 5 | 3 |  | 4
Comp | ANN/NEMO | self_biased_comp | 5 | 5 | 5
Curr_Source | ANN/NEMO | curr_source | 5 | 5 | 2
VTC (Comp+SW+Curr_source+2Caps) | ANN/NEMO | vtc | 5 | 5 | 2 |  | 4
OR_custom | ANN/NEMO | or | 3 | 5 | 5
latch_standard_cells | ANN/NEMO | latch | 3 | 5 | 5
Current_starved_inverter | ANN/NEMO | currstar_inv_delay_element | 3 | 5 | 5
inv (for the delay element) | ANN/NEMO | inv_delay_element | 3 | 5 | 5
delay_element(contains inv & currstar_inv) | ANN/NEMO | delay_elemnet | 3 | 5 | 5
TDC(contains delay_elemnets+latches+muxes) | ANN/NEMO | tdc | 5 | 5 | 4
DSA(synthesized) | ANN/NEMO | dsa | 5 | 4 | 2
IO | ANN/NEMO |  | 3 | 3 | 1
ADC (contains LVR,VTC,TDC) | ANN/NEMO | timedomainarch | 5 | 5 | 3
ADC wrapper (contains ADC,MUX,DSA) | ANN/NEMO | timedomainarch_dsa_mux | 5 | 5 | 3
regfile/SRAM memor y for the output * | ANN/NEMO | input_memory | 5 | 5 | 1
regfile/SRAM memor y for the input * | ANN/NEMO | output_memory | 5 | 5 | 1
TOP LEVEL_subarr (4subarray) | ANN/NEMO | pe16x16 | 5 | 5 | 3
Schematic status scale (0-5)
1- not started yet
2- initial schematic
3- partial transistor-level implementation
4- schematic done - charactrization needed
5- done

## TD-ANN Subblocks
Subblocks | I/F | Specs
SIPO
PISO
Column Decoder
Row Decoder
Column Driver
Row Driver
Controller
Phase generator
Clock Receiver
Global Clock drivers
Y-flash array
TD-ADC |  | 9-bit
LVR
HV-Tolerant driver
DSA
PE | # instances
Column Decoder | 1
Row Decoder | 1
Column Driver | 1
Row Driver | 1
TD-ADC | 8
Analog 4:1 mux | 8
LVR | 8
Y-flash 8x8 array | 1
Writing circuits | 8
DSA | 8
Top | Sub-hierarchy
TD-ADC
| VTC | Current sources
CT-Comparator
Switched caps
| SAR TDC | Latch comparator
Delay lines
Decoder
LVR | OTA
Power PMOS
Switch

## NDC Subblocks
Subblocks | Comment | I/F | Specs
SIPO
PISO
Column Decoder
Row Decoder
Column Driver
Row Driver
Controller
TIA (opAmp)
Clock Receiver
Global Clock
Double-Tail Comparator
DAC | Can apply bias externally
SAR logic
RC filter for bias
Analog multiplexers
Memory
Decimation
Power Consumption
DAC Subblocks: | #Instance |  |  | (per 1)
N Switches | 7 |  |  | 43uW
P Switches | 7 |  |  | 70uW
30uW
P-Switch Subblock:
Level Shifter | 7 |  |  | 30uW
5V Inverter | 3
N-Switch Subblock:
Latch | 7 |  |  | 15.2uW
Strong Inverter | 7 |  |  | 26uW
Comparator array subblock:
DT Comparator | 8 |  |  | 43uW
XOR | 8 |  |  | 31.5uW
Delay Element | 8 |  |  | 44.5uW
TIA Subblock:
Operational Amplifier | 1 |  |  | -
Latch-Memory:
DFFRQ Latch | 15 (7 In N-Switch) |  |  | 15.2uW
[5 empty] | Sampling rate | FOM | P/fs
NDC |  |  |  | 1.427mW | 91.9MHz | 61.3f | 15.69p
Critical Blocks:
DT Comparator
Level Shifter (In P-Switch subblock)
P-Switch
Operational Amplifier (Might change the design)
Delay Element

## NDC Layout
Critical Blocks | Cell Name | Top-Level Hierarchy | Library | importance (0-5) | Urgency (0-5) | schematic status(0-5) | Shared? | Layout Effort (0-5) | I/O
DT Comparator | DT_Comparator | TopView->SARComptop->CompXORTop->DT_Comparator | NEMO_Structural_model | 5 | 5 | 5 |  | 5
Delay Element | DelayStr | TopView->SARComptop->CompXORTop->DelayStr | NEMO_Structural_model | 2 | 1 | 5 |  | 1
1x Inverter | 1xInverter | TopView->SARComptop->CompXORTop->DelayStr->1xInverter | NEMO_Structural_model | 1 | 1 | 5 |  | 0
2x Inverter | 2xInverter | TopView->SARComptop->CompXORTop->DelayStr->2xInverter | NEMO_Structural_model | 1 | 1 | 5 |  | 0
4x Inverter | 4xInverter | TopView->SARComptop->CompXORTop->DelayStr->4xInverter | NEMO_Structural_model | 1 | 1 | 5 |  | 0
P-Switch | Mux_p_str | TopView->DAC_Structure->Mux_p_str | NEMO_Structural_model | 2 | 2 | 5 |  | 2
Level Shifter | LevelShifter | TopView->DAC_Structure->Mux_p_str->LevelShifter | NEMO_Structural_model | 4 | 3 | 4 |  | 4
5V Inverter | 5VInverter | TopView->DAC_Structure->Mux_p_str->LevelShifter->5VInverter | NEMO_Structural_model | 1 | 1 | 5 |  | 0
Folded- Cascode Operational Amplifier | FCOpAmp | TopView->TIA_Top->FCOpAmp | NEMO_Structural_model | 5 | 5 | 2 |  | 5
TIA | TIA_Top | TopView->TIA_Top | NEMO_Structural_model | 5 | 5 | 2 |  | 5
DAC | DAC_Structure | TopView->DAC_Structure | NEMO_Structural_model | 5 | 5 | 5 |  | 5
Loop Unrolled Chain | SARComptop | TopView->SARComptop | NEMO_Structural_model | 5 | 5 | 5 |  | 5
NDC TOP | TopView | TopView | NEMO_Structural_model | 5 | 5 | 4 |  | 5

## Activities
Task | Start | End | Chip | Collaborator | Output
Preliminary design, evaluation, and simulation of ANN basic topologies based on Y-flash. | 2024-09-01 | 2025-03-01 | ANN pathfinder | Tower (a) | Architecture definition
Definition of electrical spec of the NDC (e.g., resolution, speed, input dynamic range, etc.). Preliminary design, evaluation, and simulation of NDC based on Y-flash. | 2024-09-01 | 2025-03-01 | NDC pathfinder | Tower | Architecture definition & electrical spec
Leverage extension of Y-flash array to 128x128. | 2024-09-01 | 2025-03-01 | ANN CS-IMC |  | Basic array structure and analysis
Leverage Weebit’s ReRAM with existing chips and possibility to reuse peripherals from Y-flash design. | 2024-09-01 | 2025-03-01 | ANN CS-IMC | Weebit(b) | Experimental measurements of analog behavior of ReRAM
Development of behavioral models of the ANN and NDC architectures. | 2025-03-01 | 2025-06-01 | ANN TD-IMC | CEVA (c) | Matlab/Verilog behavioral model
ANN CS-IMC
NDC
Circuit design (schematic + layout) of ANN (Y-flash memory array, peripherals). Preliminary version of supporting interface circuits (e.g., SIPO/PISO, IO buffers). Tape out test chip. | 2025-03-01 | 2025-12-01 | ANN pathfinder | J. Shor (d) | ANN pathfinder Test chip. To be integrated by CEVA.
R. Daniel (e)
CEVA
Circuit design (schematic + layout) of 32x32 ReRAM array with basic peripherals. Tape out test chip. | 2025-03-01 | 2025-12-01 | Analog ReRAM Array | Tower | Analog ReRAM Array test chip. Standalone testing.
Weebit
Circuit design (schematic + layout) of NDC (Y-flash memory array, peripherals). Tape out test chip. | 2025-03-01 | 2025-12-01 | NDC pathfinder | CEVA | NDC pathfinder test chip. To be integrated by CEVA.
Design and development of digital controller for the ANN accelerators. | 2025-12-01 | 2026-06-01 | ANN TD-IMC |  | RTL of controller. Synthesis of RTL and physical implementation.
ANN CS-IMC
Design and development of digital controller and any digital supporting circuit (e.g., calibration) for the neuromorphic ADC or DAC | 2025-12-01 | 2026-06-01 | NDC |  | RTL of controller. Synthesis of RTL and physical implementation.
Experimental measurements of test chips | 2026-03-01 | 2026-05-01 | ANN / NDC pathfinder/ Analog ReRAM array |  | Experimental validation of initial design.
Integration of test chip with CEVA for preliminary testing of Nemo platform. | 2026-03-01 | 2026-05-01 | ANN & NDC pathfinder | CEVA | Experimental validation, Si debug on platform.
Leverage updated PDK from Tower including Weebit’s ReRAM devices. Feasibility analysis of a 1024x1024 array. (e) | 2026-03-01 | 2026-06-01 | ReRAM ANN | Weebit
Tower
Full chip integration of ANN architectures based on Y-flash. Final implementation of SIPO/PISO. Final chip tape out. | 2026-03-01 | 2026-09-01 | ANN TD-IMC | Tower | Final chip tape out.
ANN CS-IMC
Full chip integration of NDC architectures based on Y-flash. Final chip tape out. | 2026-03-01 | 2026-09-01 | NDC | Tower | Final chip tape out.
Full chip integration of ANN CS-IMC based on ReRAM (size and final implementation depend on the feasibility study) | 2026-03-01 | 2026-12-01 | ANN CS-IMC | Weebit | Final chip tape out.
Test plan, procedure coding, and integration testing. | 2026-09-01 | 2027-01-01 | ANN TD-IMC | CEVA | Test plan and description, test codes. Design validation procedures.
ANN CS-IMC
NDC
Experimental measurements and post-silicon debug of both ANN accelerators and NDC. | 2027-03-01 | 2027-06-01 | ANN TD-IMC |  | Experimental validation, Si debug at our lab.
ANN CS-IMC
NDC
Final integration with CEVA’s FPGA/DSP. | 2027-05-01 | 2027-07-01 | ANN TD-IMC | CEVA | Experimental validation, Si debug on platform.
ANN CS-IMC
NDC
Final demonstration. | 2027-07-01 | 2027-08-01 | ANN TD-IMC | WP1/2 | TBD.
ANN CS-IMC
NDC
(a) Tower will provide the CMOS technology (180 nm) and the Y-flash memristive device.
(b) Weebit will provide memory arrays available in other technology nodes so that we can leverage a possible design with Weebit’s ReRAM.
(c) J. Shor will provide initial SIPO/PISO design that will be adapted to our needs.
(d) R. Daniel will consume the SIPO/PISO.
(e) Besides the feasibility concerns of a 1024x1024 ANN. Moving into this large-scale array will require extra resources (personnel and budget).

## PDK Devices
Transistors | Caps | ESD | Resistor | Diode | BJT
nmos_18 | cmim_sl | esdp18 | rm1 | dn18 | VD5
nmos_18v_hp | cmim_sq | esdp18a | rm2 | dp18 | VDN5
pmos_5V | pwcap | esdn5a | rm3 | dn50
nmos_5V | nwcap | esdn18a | rmL | dp50
nmos_5V_hp | ch53t | esdp5 | rpmpoly3t
pmos_5V_hp | cm32t | esdn18 | rphpoly3t
pmos_18v_hp | cm33t | esdn5 | rplpoly3t
pmos_18 |  |  | rpplus_sal3t

## Pinout_TO1 (hidden)
Pin | Name | Block | Purpose | Direction | Attribute | Comment | Specs | Summary
1 | VDD | Top | Power | in | Power | Core voltage 1.8 V |  | Supply | 6
2 | VDD | Top | Power | in | Power | Core voltage 1.8 V |  | VSS | 6
3 | VSS | Top | Ground | in | Ground | Ground |  | SPI | 6
4 | VSS | Top | Ground | in | Ground | Ground |  | Clock | 1
5 | VDDIO | IO | Power | in | Power | IO voltage 5 V |  | Parallel IO | 22
6 | VDDIO | IO | Power | in | Power | IO voltage 5 V |  | Analog | 16
7 | VDDHV | Top | Power | in | Power | HV voltage 7 V | 5 V REGULATOR WITH SPIKES OF 7 V | Dig view | 8
8 | VDDHV | Top | Power | in | Power | HV voltage 7 V | 5 V REGULATOR WITH SPIKES OF 7 V | Reset | 1
9 | UCLKp | Top | Clock | in | Digital | Main clock | 1 MHz | Spare | 2
10 | UCLKn | Top | Clock | in | Digital | Main clock | REMOVE ONE | TOTAL | 68
11 | SCLK_CTRL | SPI0/1 | Clock | in | Digital | SPI clock
12 | SDI_CTRL | SPI | Data | in | Digital | SPI input
13 | SDO_CTRL | SPI | Data | out | Digital | SPI output
14 | CS_CTRL | SPI0 | Control | in | Digital | SPI0 chip select
15 | SCLK_DATA | SPI0/1 | Clock | in | Digital | SPI clock
16 | SDI_DATA | SPI | Data | in | Digital | SPI input
17 | SDO_DATA | SPI | Data | out | Digital | SPI output
18 | CS_DATA | SPI0 | Control | in | Digital | SPI0 chip select
19 | PISO_CLK | SPI1 | Control | in | Digital | SPI1 chip select
20 | PISO_DATA | SPI0/1 | Clock | in | Digital | SPI clock
21 | PISO_WR | SPI | Data | in | Digital | SPI input |  |  |  | SCLK |  | SPI0
22 | PISO_RST | SPI | Data | out | Digital | SPI output |  |  |  | SDI |  | SPI1
Pin | Name | Block | Purpose | Direction | Attribute | Comment
23 | VSS | Top | Ground | in | Ground | Ground |  |  |  | SDO |  | SPI2
24 | VSS | Top | Ground | in | Ground | Ground |  |  |  | CS0,1,2
25 | ANA<0> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
26 | ANA<1> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases |  |  |  | Add requirements of bias, resolution, noise, etc.
27 | ANA<2> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
28 | ANA<3> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
29 | ANA<4> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
30 | ANA<5> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
31 | ANA<6> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
32 | ANA<7> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
33 | ANA<8> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
34 | ANA<9> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
35 | ANA<10> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
36 | ANA<11> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
37 | ANA<12> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
38 | ANA<13> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
39 | ANA<14> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
40 | ANA<15> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
41 | DIGVIEW<0> |  | DFT | out | Digital | GPIO
42 | DIGVIEW<1> |  | DFT | out | Digital | GPIO
43 | DIGVIEW<2> |  | DFT | out | Digital | GPIO
44 | DIGVIEW<3> |  | DFT | out | Digital | GPIO
45 | DIGVIEW<4> |  | DFT | out | Digital | GPIO
46 | DIGVIEW<5> |  | DFT | out | Digital | GPIO
47 | DIGVIEW<6> |  | DFT | out | Digital | GPIO
48 | DIGVIEW<7> |  | DFT | out | Digital | GPIO
49 | SPARE<0> | Spare | Spare |  | Digital | GPIO
50 | SPARE<1> | Spare | Spare |  | Digital | GPIO
51 | SPARE<2>
52 | SPARE<3>
53 | SPARE<4>
54 | SPARE<5>
55 | SPARE<6>
56 | SPARE<7>
57 | SPARE<8>
58 | SPARE<9>
59 | SPARE<10>
60 | SPARE<11>
61 | SPARE<12>
62 | SPARE<13>
63 | SPARE<14>
64 | SPARE<15>
65 | SPARE<16>
66 | RST | Reset | Reset |  | Digital | General reset
67 | VSS | Top | Ground | in | Ground | Ground
68 | VSS | Top | Ground | in | Ground | Ground

## Pinout (hidden)
Pin | Name | Block | Purpose | Direction | Attribute | Comment | Specs | Summary
1 | VDD | Top | Power | in | Power | Core voltage |  | Supply | 6
2 | VDD | Top | Power | in | Power | Core voltage |  | VSS | 6
3 | VSS | Top | Ground | in | Ground | Ground |  | SPI | 6
4 | VSS | Top | Ground | in | Ground | Ground |  | Clock | 1
5 | VDDIO | IO | Power | in | Power | IO voltage |  | Parallel IO | 22 |  | kT/C
6 | VDDIO | IO | Power | in | Power | IO voltage |  | Analog | 16 |  | B | Cmin
7 | VDDHV | Top | Power | in | Power | HV voltage |  | Dig view | 8 |  | 4 | 0.012718
8 | VDDHV | Top | Power | in | Power | HV voltage |  | Reset | 1 |  | 5 | 0.050872
9 | UCLK | Top | Clock | in | Digital | Main clock | 1 MHz | Spare | 2 |  | 6 | 0.20349
10 | SCLK | SPI0/1 | Clock | in | Digital | SPI clock |  | TOTAL | 68 |  | 7 | 0.81396
11 | SDI | SPI | Data | in | Digital | SPI input |  |  |  |  | 8 | 3.2558
12 | SDO | SPI | Data | out | Digital | SPI output |  |  |  |  | 9 | 13.0233
13 | CS<0> | SPI0 | Control | in | Digital | SPI0 chip select |  |  |  |  | 10 | 52.0933
14 | CS<1> | SPI1 | Control | in | Digital | SPI1 chip select |  |  |  |  | 11 | 208.373
15 | CS<2> | SPI2 | Control | in | Digital | SPI2 chip select |  |  |  |  | 12 | 833.4921
16 | DATA<0> | Parallel IO | Data | inout | Digital | Parallel data half-duplex |  |  |  |  | 13 | 3333.9684
17 | DATA<1> | Parallel IO | Data | inout | Digital | Parallel data half-duplex
18 | DATA<2> | Parallel IO | Data | inout | Digital | Parallel data half-duplex
19 | DATA<3> | Parallel IO | Data | inout | Digital | Parallel data half-duplex
20 | DATA<4> | Parallel IO | Data | inout | Digital | Parallel data half-duplex
21 | DATA<5> | Parallel IO | Data | inout | Digital | Parallel data half-duplex |  |  |  | SCLK | SPI0
22 | DATA<6> | Parallel IO | Data | inout | Digital | Parallel data half-duplex |  |  |  | SDI | SPI1
23 | DATA<7> | Parallel IO | Data | inout | Digital | Parallel data half-duplex |  |  |  | SDO | SPI2
24 | CA<0> | Parallel IO | Control | in | Digital | Command/address |  |  |  | CS0,1,2
25 | CA<1> | Parallel IO | Control | in | Digital | Command/address
26 | CA<2> | Parallel IO | Control | in | Digital | Command/address
27 | CA<3> | Parallel IO | Control | in | Digital | Command/address
28 | CA<4> | Parallel IO | Control | in | Digital | Command/address
29 | CA<5> | Parallel IO | Control | in | Digital | Command/address
30 | CA<6> | Parallel IO | Control | in | Digital | Command/address
31 | CA<7> | Parallel IO | Control | in | Digital | Command/address
32 | CLKI_P | Parallel IO | Clock | in | Digital | Differential input clock
33 | CLKI_P | Parallel IO | Clock | in | Digital | Differential input clock
34 | CLKO_P | Parallel IO | Clock | out | Digital | Differential output clock
35 | CLKO_N | Parallel IO | Clock | out | Digital | Differential output clock
36 | Valid | Parallel IO | Parallel IO | inout | Digital | Valid
37 | WE | Parallel IO | Parallel IO | in | Digital | Write enable
38 | VSS | Top | Ground | in | Ground | Ground
39 | VSS | Top | Ground | in | Ground | Ground
40 | ANA<0> | Array | Sense/Force | inout | Analog | Bias or sense | Y-flash array testing, bias readout, force biases
41 | ANA<1> | Array | Sense/Force | inout | Analog | Bias or sense
42 | ANA<2> | Array | Sense/Force | inout | Analog | Bias or sense
43 | ANA<3> | Array | Sense/Force | inout | Analog | Bias or sense
44 | ANA<4> | Array | Sense/Force | inout | Analog | Bias or sense
45 | ANA<5> | Array | Sense/Force | inout | Analog | Bias or sense
46 | ANA<6> | Array | Sense/Force | inout | Analog | Bias or sense
47 | ANA<7> | Array | Sense/Force | inout | Analog | Bias or sense
48 | ANA<8> | Array | Sense/Force | inout | Analog | Bias or sense
49 | ANA<9> | Array | Sense/Force | inout | Analog | Bias or sense
50 | ANA<10> | Array | Sense/Force | inout | Analog | Bias or sense
51 | ANA<11> | Array | Sense/Force | inout | Analog | Bias or sense
52 | ANA<12> | Array | Sense/Force | inout | Analog | Bias or sense
53 | ANA<13> | Array | Sense/Force | inout | Analog | Bias or sense
54 | ANA<14> | Array | Sense/Force | inout | Analog | Bias or sense
55 | ANA<15> | Array | Sense/Force | inout | Analog | Bias or sense
56 | DIGVIEW<0> |  | DFT | out | Digital | GPIO | Reuse SPI driver
57 | DIGVIEW<1> |  | DFT | out | Digital | GPIO
58 | DIGVIEW<2> |  | DFT | out | Digital | GPIO
59 | DIGVIEW<3> |  | DFT | out | Digital | GPIO
60 | DIGVIEW<4> |  | DFT | out | Digital | GPIO
61 | DIGVIEW<5> |  | DFT | out | Digital | GPIO
62 | DIGVIEW<6> |  | DFT | out | Digital | GPIO
63 | DIGVIEW<7> |  | DFT | out | Digital | GPIO
64 | SPARE<0> | Spare | Spare |  | Digital | GPIO
65 | SPARE<1> | Spare | Spare |  | Digital | GPIO
66 | RST | Reset | Reset |  | Digital | General reset
67 | VSS | Top | Ground | in | Ground | Ground
68 | VSS | Top | Ground | in | Ground | Ground
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to split the SPI into two independent

## IO-Pins-Dima
Pin | Name | Block | Purpuse | direction | Attribute(analog/digital) | shared(between TOP_ANN and stand alone block) | Summary -MCP
1 | vssx | TOP_ANN | ground | in | ground | yes | 4*2=8 | ground
2 | vssx | TOP_ANN | ground | in | ground | yes | 4*2=8 | RF
3 | vssx | TOP_ANN | ground | in | ground | yes | 6+10=16 | Power/Biases | seperate between the powers + add the inputs for the stand alone blocks - maybe all of them from the sipo
4 | vssx | TOP_ANN | ground | in | ground | yes | 8*2+6*2=28 | digital
5 | vssx | TOP_ANN | ground | in | ground | yes | 60 pins
6 | vssx | TOP_ANN | ground | in | ground | yes
7 | vssx | TOP_ANN | ground | in | ground | yes | Package
8 | vssx | TOP_ANN | ground | in | ground | yes | 8
9 | vccx | TOP_ANN | power | in | power | yes
10 | vccx | TOP_ANN | power | in | power | yes
11 | vccy | TOP_ANN | power | in | power | yes
12 | vcch_wl | TOP_ANN | power | in | power | yes
13 | vcch_bl | TOP_ANN | power | in | power | yes
14 | delta_vb | TOP_ANN | bias | in | power | yes
15 | lvr_vb | TOP_ANN | bias | in | analog | yes
16 | lvr_vcm | TOP_ANN | bias | in | analog | yes
17 | bl_pad | TOP_ANN | dft | in/out | analog | yes
18 | tdc_vb | TOP_ANN | bias | in | analog | yes
19 | v_erase | TOP_ANN | bias | in | analog | yes
20 | v_read | TOP_ANN | bias | in | analog | yes
21 | v_write | TOP_ANN | bias | in | analog | yes
22 | vtc_vb | TOP_ANN | bias | in | analog | yes
23 | vth | TOP_ANN | bias | in | analog | yes
24 | bl_vdc | TOP_ANN | bias | in | analog | yes
25 | clk_piso | TOP_ANN | clock | in | digital | yes
26 | clk_sipo | TOP_ANN | clock | in | digital | no
27 | sipo_in | TOP_ANN | data | in | digital | no
28 | reset | TOP_ANN | logic | in | digital | no
29 | s0 | TOP_ANN | logic | in | digital | no
30 | s1 | TOP_ANN | logic | in | digital | no
31 | s2 | TOP_ANN | logic | in | digital | no
32 | set | TOP_ANN | logic | in | digital | no
33 | shift | TOP_ANN | logic | in | digital | yes
34 | cs | TOP_ANN | logic | in | digital | no
35 | rst_dsa | TOP_ANN | logic | in | digital | no
36 | rst_piso | TOP_ANN | logic | in | digital | yes
37 | rst_sipo | TOP_ANN | logic | in | digital | no
38 | s0_dft | TOP_ANN | logic | in | digital | no
39 | s1_dft | TOP_ANN | logic | in | digital | no
40 | b0_dft | TOP_ANN | logic | in | digital | no
41 | b1_dft | TOP_ANN | logic | in | digital | no
42 | b2_dft | TOP_ANN | logic | in | digital | no
43 | piso_out | TOP_ANN | logic | out | digital | no
44 | sipo_out | TOP_ANN | logic | out | digital | no
45 | reset_sa | Stand Alone | logic | in | digital | no
46 | set_sa | Stand Alone | logic | in | digital | no
47 | clk_sa | Stand Alone | clk | in | digital | no
48 | input_sa | Stand Alone | data | in | digital | no
49 | s0_dft_sa | Stand Alone | logic | in | digital | no
50 | s1_dft_sa | Stand Alone | logic | in | digital | no
51 | piso_out_sa | Stand Alone | logic | out | digital | no
52 | clk | TOP_ANN | clock | in | RF | no
53 | pulse | TOP_ANN | pulse | in | RF | no
54 | dft0 | TOP_ANN | logic | out | RF | no
55 | dft1 | TOP_ANN | logic | out | RF | no
56 | dft_0_sa | Stand Alone | dft | out | RF | no
57 | dft_1_sa | Stand Alone | dft | out | RF | no
58
59
60
61 | [35 empty] | E(xtra) |  | Note:
62 | [15 empty] | E | L | L | L | L | S | G | B | B | B | G | S | L | L | L | L | E |  |  |  | L(ogic) |  | Pad numbers do not correspond to pin list
63 | [16 empty] | s0_dft | s1_dft | piso_out | sipo_out |  | vssx | vtc_vb | bl_pad | tdc_vb | vssx |  | v_erase | rst_sipo | rst_dsa | cs |  |  |  |  | G(round)
64 | [35 empty] | B(ias)
65 | [35 empty] | S(ignal)
66 | [35 empty] | P(ower)
67
[13 empty] | E | [21 empty] | E |  |  | PVPP: General Analog/High Voltage
[13 empty] | L | b0_dft | [19 empty] | s0 | L |  |  | PAL: Logic/RF
[13 empty] | L | b1_dft | [19 empty] | s1 | L |  |  | PVDI: vccx
[13 empty] | L | b2_dft | [19 empty] | s2 | L |  |  | PVDA: vccy
[13 empty] | S | dft0_s1 | [19 empty] | dft0 | S |  |  | PV0F: vssx
[13 empty] | G | vssx | [19 empty] | vssx | G
[13 empty] | B | vth | [19 empty] | delta_vb | B
[13 empty] | B | v_read | [19 empty] | vccy | B
[13 empty] | P | vccy | [19 empty] | vccx | P
[13 empty] | B | v_write | [19 empty] | vcch_wl | B
[13 empty] | B | bl_vdc | [19 empty] | vcch_bl | B
[13 empty] | G | vssx | [19 empty] | vssx | G
[13 empty] | S | dft1_sa | [19 empty] | dft1 | S
[13 empty] | L | reset_sa | [19 empty] | clk_piso | L
[13 empty] | L | set_sa | [19 empty] | shift | L
[13 empty] | L | clk_sa | [19 empty] | rst_piso | L
[13 empty] | E | [21 empty] | E
[17 empty] | s0_dft_sa | s1_dft_s1 | piso_out_sa | input_sa | pulse | vssx | lvr_vcm | vccx | lvr_vb | vssx | clk | set | reset | sipo_in | clk_sipo
[16 empty] | E | L | L | L | L | S | G | B | P | B | G | S | L | L | L | L | E
??
[20 empty] | ?? | c |  |  | c |  |  | c |  | c | c | c | c
[17 empty] | label | label | label | label | v | v | v | v | v | v | v | v | label | label | label |  |  |  |  | E(xtra) |  | Note:
[16 empty] | E | L | L | L | L | S | G | B | B | B | G | S | L | L | L | L | E |  |  |  | L(ogic) |  | Pad numbers do not correspond to pin list
[17 empty] | s0_dft | s1_dft | rst_dsa | s3_dft | dft0 | vssx | vtc_vb | delta_vb | tdc_vb | vssx | dft1 | v_erase | s2_dft | reset | b2_dft |  |  |  |  | G(round)
B(ias)
S(ignal)
P(ower)
[13 empty] | E | [21 empty] | E |  |  |  |  | PVPP: General Analog/High Voltage
[11 empty] | c | label | L | s0 | [19 empty] | rst_piso | L | label | c | serial_out?? |  | PAL: Logic/RF
[11 empty] | c | label | L | s1 | [19 empty] | piso_out | L | label | c |  |  | PVDI: vccx
[11 empty] | c | label | L | s2 | [19 empty] | shift | L | label | c |  |  | PVDA: vccy
[11 empty] | c | label | S | clk | [19 empty] | clk_piso | S | label | c |  |  | PV0F: vssx
[12 empty] | v | G | vssx | [19 empty] | vssx | G | v
[12 empty] | v | B | vth | [19 empty] | bl_pad | B | v | c
[12 empty] | v | B | v_read | [19 empty] | vccy | B | v
[12 empty] | v | P | vccy | [19 empty] | vccx | P | v
[11 empty] | c | v | B | lvr_vcm | [19 empty] | vcch_wl | B | v
[11 empty] | c | v | B | lvr_vb | [19 empty] | vcch_bl | B | v
[12 empty] | v | G | vssx | [19 empty] | vssx | G | v
[11 empty] | c | label | S | pulse | [20 empty] | S |  | c
[11 empty] | c | label | L | b1_dft | [20 empty] | L
[11 empty] | c | label | L | set | [20 empty] | L
[11 empty] | c | label | L | b0_dft | [20 empty] | L
[13 empty] | E | [21 empty] | E
[10 empty] | reset_sa |  | s0_dft_sa | s1_dft_s1
[11 empty] | clk_sa |  |  |  |  | L: sipo_in; L: clk_sipo; L: sipo_out; L: cs; S: rst_sipo; G: vssx; B: v_write; B: vccx; B: bl_vdc; G: vssx
[10 empty] | set_sa | [5 empty] | E | L | L | L | L | S | G | B | P | B | G | S | L | L | L | L | E
[12 empty] | dft1_sa |  |  |  | L: label; L: label; L: label; L: label; S: label; G: v; B: v; P: v; B: v; G: v
[17 empty] | c | c |  |  | c |  | c |  | c |  | c | c
[10 empty] | dft0_s1 | input_sa | piso_out_sa
[20 empty] | PAL-R | PAL-R | PAL-R | PAL-R | PAL-R | PV0F | PVDI | PAL-R | PVPP-PAD | PV0F | PAL-R | PAL-R | PAL-R | PAL-R | PAL-R
[33 empty] | v | v | bar: L to E
[20 empty] | PAL-R | PAL-R | PAL-R | PAL-R | PAL-PAD | PV0F | PAL-R | PAL-R | PAL-R | PV0F | PAL-PAD | PVPP-PAD | PAL-R | PAL-R | PAL-R
[20 empty] | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 68 | 67 | 66 | 65 | 64 | 63 | 62
[20 empty] | L | L | L | L | S | G | P | P | P | G | S | L | L | L | L
[20 empty] | s0_dft | s1_dft | rst_dsa | s3_dft | dft0_buff | vssx | vtc_vb | delta_vb | tdc_vb | vssx | dft1_buff | v_erase | s2_dft | reset | b2_dft
[14 empty] | PAL-R | v | PAL-R | 11 | L | s0_p | [15 empty] | rst_piso | L | 59 | PAL-R | v | PAL-R
[14 empty] | PAL-R | v | PAL-R | 12 | L | s1_p | [15 empty] | piso_out | L | 58 | PAL-PAD | v | PAL-R
[14 empty] | PAL-R | v | PAL-R | 13 | L | s2_p | [15 empty] | shift | L | 57 | PAL-R | v | PAL-R
[14 empty] | PAL-R | v | PAL-R | 14 | S | clk | [15 empty] | clk_piso | S | 56 | PAL-R | v | PAL-PAD
[14 empty] | PV0F | v | PV0F | 15 | G | vssx | [15 empty] | vssx | G | 55 | PV0F | v | PV0F
[14 empty] | PVPP-PAD | v | PAL-R | 16 | P | vth | [15 empty] | pad | P | 54 | PVPP-PAD | v | PVPP-PAD
[14 empty] | PVDI | v | PVPP-PAD | 17 | P | v_read | [15 empty] | vccy | P | 53 | PVDA | v | PVPP-PAD
[14 empty] | PVDA | v | PVDA | 18 | P | vccy | [15 empty] | vccx | P | 52 | PVDI | v | PVDI
[14 empty] | PVPP-PAD | v | PAL-R | 19 | P | lvr_cm | [15 empty] | vcch_wl | P | 51 | PVPP-PAD | v | PVDA
[14 empty] | PVPP-PAD | v | PAL-R | 20 | P | lvr_vb | [15 empty] | vcch_bl | P | 50 | PVPP-PAD | v | PVPP-PAD
[14 empty] | PV0F | v | PV0F | 21 | G | vssx | [15 empty] | vssx | G | 49 | PV0F | v | PV0F
[14 empty] | PAL-R | v | PAL-R | 22 | S | pulse | [16 empty] | S | 48 |  |  | PAL-PAD
[14 empty] | PAL-R | v | PAL-R | 23 | L | b1_dft | [16 empty] | L | 47 |  |  | PAL-R
[14 empty] | PAL-R | v | PAL-R | 24 | L | set | [16 empty] | L | 46 |  |  | PAL-R
[14 empty] | PAL-R | v | PAL-R | 25 | L | b0_dft | [16 empty] | L | 45 |  |  | PAL-R
[20 empty] | sipo_in | clk_sipo | sipo_out | cs |  | vssx | v_write | vccx | bl_vdc | vssx |  | rst_sipo
[20 empty] | L | L | L | L | S | G | P | P | P | G | S | L | L | L | L
[20 empty] | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
[20 empty] | PAL-R | PAL-R | PAL-PAD | PAL-R |  | PV0F | PVPP-PAD | PVDI | PVPP-PAD | PV0F |  | PAL-R
[20 empty] | v | v | v | v |  | v | v | v | v | v |  | v
[20 empty] | PAL-R | PAL-R | PAL-R | PAL-R | PAL-PAD | PV0F | PAL-R | PVDA | PAL-R | PV0F | PAL-PAD | PAL-R | PAL-R | PAL-R | PAL-R
[21 empty] | PAL-R | PAL-R | PAL-R | PAL-R | PAL-R | PV0F | PVDI | PAL-R | PVPP-PAD | PV0F | PAL-R | PAL-R | PAL-R | PAL-R | PAL-R
[35 empty] | v |  |  |  |  | GND |  | Power | signals | empty | bar: L 29 to L 42
[21 empty] | PAL-R | PAL-R | PAL-R | PAL-R | PAL-PAD | PV0F | PAL-R | PAL-R | PAL-R | PV0F | PAL-PAD | PVPP-PAD | PAL-R | PAL-R | PAL-R
[21 empty] | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 68 | 67 | 66 | 65 | 64 | 63 | 62
[21 empty] | L | L | L | L | S | G | P | P | P | G | S | L | L | L | L
[21 empty] | s0_dft | s1_dft | rst_dsa | s3_dft | dft0_buff | vssx | vtc_vb | delta_vb | tdc_vb | vssx | dft1_buff | v_erase | s2_dft | reset | b2_dft
[15 empty] | PAL-R | v | PAL-R | 11 | L | s0_p | [15 empty] | rst_piso | L | 59 | PAL-R | v | PAL-R
[15 empty] | PAL-R | v | PAL-R | 12 | L | s1_p | [15 empty] | piso_out | L | 58 | PAL-PAD | v | PAL-R
[15 empty] | PAL-R | v | PAL-R | 13 | L | s2_p | [15 empty] | shift | L | 57 | PAL-R | v | PAL-R
[15 empty] | PAL-R | v | PAL-R | 14 | S | clk | [15 empty] | clk_piso | S | 56 | PAL-R | v | PAL-PAD
[15 empty] | PV0F | v | PV0F | 15 | G | vssx | [15 empty] | vssx | G | 55 | PV0F | v | PV0F
[15 empty] | PVPP-PAD | v | PAL-R | 16 | P | vth | [15 empty] | pad | P | 54 | PVPP-PAD | v | PVPP-PAD
[15 empty] | PVDI | v | PVPP-PAD | 17 | P | v_read | [15 empty] | vccy | P | 53 | PVDA | v | PVPP-PAD
[15 empty] | PVDA | v | PVDA | 18 | P | vccy | [15 empty] | vccx | P | 52 | PVDI | v | PVDI
[15 empty] | PVPP-PAD | v | PAL-R | 19 | P | lvr_cm | [15 empty] | vcch_wl | P | 51 | PVPP-PAD | v | PVDA
[15 empty] | PVPP-PAD | v | PAL-R | 20 | P | lvr_vb | [15 empty] | vcch_bl | P | 50 | PVPP-PAD | v | PVPP-PAD
[15 empty] | PV0F | v | PV0F | 21 | G | vssx | [15 empty] | vssx | G | 49 | PV0F | v | PV0F
[15 empty] | PAL-R | v | PAL-R | 22 | S | pulse | [16 empty] | S | 48 |  |  | PAL-PAD
[15 empty] | PAL-R | v | PAL-R | 23 | L | b1_dft | [16 empty] | L | 47 |  |  | PAL-R
[15 empty] | PAL-R | v | PAL-R | 24 | L | set | [16 empty] | L | 46 |  |  | PAL-R
[15 empty] | PAL-R | v | PAL-R | 25 | L | b0_dft | [16 empty] | L | 45 |  |  | PAL-R
[21 empty] | sipo_in | clk_sipo | sipo_out | cs |  | vssx | v_write | vccx | bl_vdc | vssx |  | rst_sipo
[21 empty] | L | L | L | L | S | G | P | P | P | G | S | L | L | L | L
[21 empty] | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42
[21 empty] | PAL-R | PAL-R | PAL-PAD | PAL-R |  | PV0F | PVPP-PAD | PVDI | PVPP-PAD | PV0F |  | PAL-R
[21 empty] | v | v | v | v |  | v | v | v | v | v |  | v
[21 empty] | PAL-R | PAL-R | PAL-R | PAL-R | PAL-PAD | PV0F | PAL-R | PVDA | PAL-R | PV0F | PAL-PAD | PAL-R | PAL-R | PAL-R | PAL-R
9
8
7
6
5
4
3
2
1
68
67
66
65
64
63
62
61
60
59
588
57
56
55
54
53
52
51
50
49
48
47
46
45
44
43
42
41
40
39
37
36
38
34
33
35
31
32
29
30
27
28
25
26
23
24
21
22
19
20
17
18
15
16
13
14
12
10
11

## SA_Interface_Nov
Pin | Name | direction
1 | vssx | in
2 | vccx | in | Analog - pins
3 | vccy | in | Digital pins
4 | vcch_wl | in
5 | vcch_bl | in
6 | delta_vb | in
7 | lvr_vb | in
8 | lvr_vcm | in
9 | bl_pad | in/out
10 | tdc_vb | in
11 | v_erase | in
12 | v_read | in
13 | v_write | in
14 | vtc_vb | in
15 | vth | in
16 | bl_vdc | in
17 | reset | in
18 | s0 | in
19 | s1 | in
20 | s2 | in
22 | clk | in
23 | pulse | in
24 | in_valid | out
25 | ADC_0 [6:0] | out
26 | ADC_1 [6:0] | out
27 | ADC_2 [6:0] | out
28 | ADC_2 [6:0] | out
29
30

## Pinout_Dima
Pin | Name | Block | Purpose | Direction | Attribute | Voltage Domain | Frequency | Type | Comment | Specs | Summary
1 | Unused | [9 empty] | Supply | 6
2 | s0_p | [9 empty] | VSS | 6
3 | s1_p | Top | Power | in | Power |  |  |  | Core voltage 1.8 V |  | SPI | 6
4 | s2_p | Top | Power | in | Power |  |  |  | Core voltage 1.8 V |  | Clock | 1
5 | clk | Top | Ground | in | Ground |  |  |  | Ground |  | Parallel IO | 22
6 | vssx | Top | Ground | in | Ground |  |  |  | Ground |  | Analog | 16
7 | vth | IO | Power | in | Power |  |  |  | IO voltage 5 V | 5 V REGULATOR WITH SPIKES OF 7 V | Dig view | 8
8 | v_read | IO | Power | in | Power |  |  |  | IO voltage 5 V | 5 V REGULATOR WITH SPIKES OF 7 V | Reset | 1
9 | vccy | Top | Power | in | Power |  |  |  | HV voltage 7 V | 1 MHz | Spare | 2
10 | lvr_cm | Top | Power | in | Power |  |  |  | HV voltage 7 V | REMOVE ONE | TOTAL | 68
11 | lvr_vb | Top | Clock | in | Digital |  |  |  | Main clock
12 | vssx | Top | Clock | in | Digital |  |  |  | Main clock
13 | pulse | SPI0/1 | Clock | in | Digital |  |  |  | SPI clock
14 | b1_dft | SPI | Data | in | Digital |  |  |  | SPI input
15 | set | SPI | Data | out | Digital |  |  |  | SPI output
16 | b0_dft | SPI0 | Control | in | Digital |  |  |  | SPI0 chip select
17 | Unused | SPI0/1 | Clock | in | Digital |  |  |  | SPI clock
18 | Unused | SPI | Data | in | Digital |  |  |  | SPI input
19 | Unused | SPI | Data | out | Digital |  |  |  | SPI output
20 | CS_DATA | SPI0 | Control | in | Digital |  |  |  | SPI0 chip select
21 | PISO_CLK | SPI1 | Control | in | Digital |  |  |  | SPI1 chip select
22 | PISO_DATA | SPI0/1 | Clock | in | Digital |  |  |  | SPI clock
Pin | PISO_WR | SPI | Data | in | Digital |  |  |  | SPI input
23 | PISO_RST | SPI | Data | out | Digital |  |  |  | SPI output
24
25 | VSS | Top | Ground | in | Ground |  |  |  | Ground | Y-flash array testing, bias readout, force biases
26 | VSS | Top | Ground | in | Ground |  |  |  | Ground | Y-flash array testing, bias readout, force biases
27 | ANA<0> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
28 | ANA<1> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
29 | ANA<2> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
30 | ANA<3> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
31 | ANA<4> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
32 | ANA<5> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
33 | ANA<6> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
34 | ANA<7> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
35 | ANA<8> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
36 | ANA<9> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
37 | ANA<10> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
38 | ANA<11> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
39 | ANA<12> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
40 | ANA<13> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense | Y-flash array testing, bias readout, force biases
41 | ANA<14> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense
42 | ANA<15> | Array | Sense/Force | inout | Analog |  |  |  | Bias or sense
43 | DIGVIEW<0> |  | DFT | out | Digital |  |  |  | GPIO
44 | DIGVIEW<1> |  | DFT | out | Digital |  |  |  | GPIO
45 | DIGVIEW<2> |  | DFT | out | Digital |  |  |  | GPIO
46 | DIGVIEW<3> |  | DFT | out | Digital |  |  |  | GPIO
47 | DIGVIEW<4> |  | DFT | out | Digital |  |  |  | GPIO
48 | DIGVIEW<5> |  | DFT | out | Digital |  |  |  | GPIO
49 | DIGVIEW<6> |  | DFT | out | Digital |  |  |  | GPIO
50 | DIGVIEW<7> |  | DFT | out | Digital |  |  |  | GPIO
51 | SPARE<0> | Spare | Spare |  | Digital |  |  |  | GPIO
52 | SPARE<1> | Spare | Spare |  | Digital |  |  |  | GPIO
53 | SPARE<4>
54 | SPARE<5>
55 | SPARE<6>
56 | SPARE<7>
57 | SPARE<8>
58 | SPARE<9>
59 | SPARE<10>
60 | SPARE<11>
61 | SPARE<12>
62 | SPARE<13>
63 | SPARE<14>
64 | SPARE<15>
65 | SPARE<16>
66 | RST | Reset | Reset |  | Digital |  |  |  | General reset
67 | VSS | Top | Ground | in | Ground |  |  |  | Ground
68 | VSS | Top | Ground | in | Ground |  |  |  | Ground

## Pinout_Dima (2)
Pin | Name | Block | Purpose | Direction | Attribute | Voltage Domain | Frequency | Type | Comment | Specs | Summary
1 | delta_vb |  | bias | in | Analog | [VSS,VDD] |  |  |  |  | Supply | 6
2 | vtc_vb |  | bias | in | Analog | [VSS-VDD] |  |  |  |  | VSS | 6 | Summary -MCP
3 | vssx | Top | Ground | in | Ground | VSS |  |  |  |  | SPI | 6 | 4*2=8 | ground
4 | dft0_buff | Top | dft | out | Digital | [5 empty] | Clock | 1 | 5 | RF
5 | s3_dft | Top | control | in | Digital | [5 empty] | Parallel IO | 22 | 6+10=16 | Power/Biases
6 | rst_dsa | Top | reset | in | Digital | [5 empty] | Analog | 16 | 21 | digital
7 | s1_dft | IO | control | in | Digital | [5 empty] | Dig view | 8 | 50pins
8 | s0_dft | IO | control | in | Digital | [5 empty] | Reset | 1
9 | Unused | Top | [8 empty] | Spare | 2
10 | Unused | Top | [8 empty] | TOTAL | 68
11 | s0_p | Top | control | in | Digital
12 | s1_p | Top | control | in | Digital
13 | s2_p | SPI0/1 | control | in | Digital
14 | clk | SPI | Clock | in | Digital
15 | vssx | SPI | Ground | in | Ground | VSS
16 | vth | SPI0 | bias | in | Analog | [VSS,VDD]
17 | v_read | SPI0/1 | bias | in | Analog | [VDD,3.3V]
18 | vccy | SPI | Power | in | Power | VDD (1.8V)
19 | lvr_cm | SPI | bias | in | Analog | [VSS,VDD]
20 | lvr_vb | SPI0 | bias | in | Analog | [VSS,VDD]
21 | vssx | SPI1 | Ground | in | Ground | VSS
22 | pulse | SPI0/1 | control | in | Digital
Pin | PISO_WR | SPI |  | in
23 | b1_dft | SPI | control | in | Digital
24 | set |  | control | in | Digital
25 | b0_dft | Top | control | in | Digital
26 | Unused | Top
27 | Unused | Top
28 | sipo_in | Array | data | in
29 | clk_sipo | Array | Clock | in
30 | sipo_out | Array | data | out
31 | cs | Array | control | in
32 | Unused | Array
33 | vssx | Array | Ground | in | Ground | VSS
34 | v_write | Array | bias | in | Analog | [VSS,5V]
35 | vccx | Array | Power | in | Power | VDD (1.8V)
36 | bl_vdc | Array | bias | in | Analog | [VSS,VDD]
37 | vssx | Array | Ground | in | Ground | VSS
38 | Unused | Top
39 | Unused | Top
40 | Unused | Top
41 | Unused | Top
42 | Unused | Top
43 | Unused | Top
44 | Unused | Top
45 | Unused | Top
46 | Unused | Top
47 | Unused | Top
48 | Unused | Top
49 | vssx |  | Ground | in | Ground | VSS
50 | vcch_bl |  | Power | in | Power | [VSS,7V] |  |  | to pass the 7
51 | vcch_wl | Spare | Power | in | Power | [VSS,5V] |  |  | to pass the 5
52 | vccx | Spare | Power | in | Power | VDD (1.8V)
53 | vccy |  | Power | in | Power | VDD (1.8V)
54 | pad |  | bias | in/out | Analog
55 | vssx |  | Ground | in | Ground | VSS
56 | clk_piso |  | Clock | in | Digital
57 | shift |  | control | in | Digital
58 | piso_out |  | data | out | Digital
59 | rst_piso |  | reset | in | Digital
60 | Unused | Top
61 | Unused | Top
62 | b2_dft |  | control | in | Digital
63 | reset |  | reset | in | Digital
64 | s2_dft |  | control | in | Digital
65 | v_erase |  | Power | in | Analog | [VSS,7V] |  |  | for short period
66 | dft1_buff | Reset | dft | out | Digital
67 | vssx | Top | Ground | in | Ground | VSS
68 | tdc_vb | Top | bias | in | Analog | [VSS,VDD]

## Blocks Interface - Digital
Pin | Name | Block | Purpose | Direction | Attribute | Voltage Domain | block |  | Digital blocks list
1 | delta_vb |  | bias | in | Analog | [VSS,VDD]
2 | vtc_vb |  | bias | in | Analog | [VSS-VDD]
3 | vssx | Top | Ground | in | Ground | VSS |  |  | dft per ADC
4 | dft0_buff | Top | dft | out | Digital |  | DFT - All | We're intersted with the blue for now.
5 | s3_dft | Top | control | in | Digital |  | dft per ADC
6 | rst_dsa | Top | reset | in | Digital |  | DSA
7 | s1_dft | IO | control | in | Digital |  | dft per ADC
8 | s0_dft | IO | control | in | Digital |  | dft per ADC
9 | Unused | Top
10 | Unused | Top
11 | s0_p | Top | control | in | Digital |  | Array with Muxes
12 | s1_p | Top | control | in | Digital |  | Array with Muxes
13 | s2_p | SPI0/1 | control | in | Digital |  | Array with Muxes
14 | clk | SPI | Clock | in | Digital |  | Clock Generator
15 | vssx | SPI | Ground | in | Ground | VSS
16 | vth | SPI0 | bias | in | Analog | [VSS,VDD]
17 | v_read | SPI0/1 | bias | in | Analog | [VDD,3.3V]
18 | vccy | SPI | Power | in | Power | VDD (1.8V)
19 | lvr_cm | SPI | bias | in | Analog | [VSS,VDD]
20 | lvr_vb | SPI0 | bias | in | Analog | [VSS,VDD] |  |  | DSA
21 | vssx | SPI1 | Ground | in | Ground | VSS
22 | pulse | SPI0/1 | control | in | Digital |  | Array with Muxes
Pin | PISO_WR | SPI |  | in
23 | b1_dft | SPI | control | in | Digital |  | DFT - All
24 | set |  | control | in | Digital |  | Clock Generator
25 | b0_dft | Top | control | in | Digital |  | DFT - All
26 | Unused | Top
27 | Unused | Top
28 | sipo_in | Array | data | in |  |  | SIPO
29 | clk_sipo | Array | Clock | in |  |  | SIPO
30 | sipo_out | Array | data | out |  |  | SIPO
31 | cs | Array | control | in |  |  | SIPO
32 | Unused | Array
33 | vssx | Array | Ground | in | Ground | VSS
34 | v_write | Array | bias | in | Analog | [VSS,5V]
35 | vccx | Array | Power | in | Power | VDD (1.8V) |  |  | SIPO
36 | bl_vdc | Array | bias | in | Analog | [VSS,VDD]
37 | vssx | Array | Ground | in | Ground | VSS
38 | Unused | Top
39 | Unused | Top
40 | Unused | Top
41 | Unused | Top
42 | Unused | Top
43 | Unused | Top
44 | Unused | Top
45 | Unused | Top
46 | Unused | Top
47 | Unused | Top
48 | Unused | Top
49 | vssx |  | Ground | in | Ground | VSS
50 | vcch_bl |  | Power | in | Power | [VSS,7V]
51 | vcch_wl | Spare | Power | in | Power | [VSS,5V]
52 | vccx | Spare | Power | in | Power | VDD (1.8V)
53 | vccy |  | Power | in | Power | VDD (1.8V)
54 | pad |  | bias | in/out | Analog |  |  |  | PISO
55 | vssx |  | Ground | in | Ground | VSS
56 | clk_piso |  | Clock | in | Digital |  | PISO
57 | shift |  | control | in | Digital |  | PISO
58 | piso_out |  | data | out | Digital |  | PISO
59 | rst_piso |  | reset | in | Digital |  | PISO
60 | Unused | Top
61 | Unused | Top
62 | b2_dft |  | control | in | Digital |  | DFT- All
63 | reset |  | reset | in | Digital |  | Clock Generator
64 | s2_dft |  | control | in | Digital |  | dft per ADC
65 | v_erase |  | Power | in | Analog | [VSS,7V]
66 | dft1_buff | Reset | dft | out | Digital |  | DFT - All
67 | vssx | Top | Ground | in | Ground | VSS
68 | tdc_vb | Top | bias | in | Analog | [VSS,VDD]
DFT - ALL
Clk Generator
Array with muxes

## Interface - Dima
Pin | Name | Block | Purpuse | Direction
#0# | vccx | All | Power | in |  | General Notes:
#0# | vssx | All | Ground | in |  | 1- all digital inputs (such as the select bit for all of the muxes) comes from the controller
1 | input | TDC | data | in |  | 2- dft block ---> dft controller
2 | ref | TDC | pulse | in | Need another 1bit/2bits MSB --> another block | 3- Digital shift & accumlate : Synthesized
3 | bias | TDC | bias | in
4 | B<0> | TDC | logic | out
5 | B<1> | TDC | logic | out
6 | B<2> | TDC | logic | out
7 | B<3> | TDC | logic | out
8 | B<4> | TDC | logic | out
9 | B<5> | TDC | logic | out
10 | B<6> | TDC | logic | out
14 | bias | TDC_ref | bias | in
15 | phase | TDC_ref | logic | in
16 | out | TDC_ref | logic | out
17 | input | VTC | data | in
18 | phi1 | VTC | logic | in | replace the comp with inv & control its threshold
19 | phi2 | VTC | logic | in | Add a precharging phase -> phi3
20 | phir | VTC | logic | in | IDAC?
21 | vth | VTC | bias | in | Fix the voltage drop: bootstrap & charge injection
22 | comp_bias | VTC | bias | in
23 | discharge_bias | VTC | bias | in
24 | out | VTC | logic | out
25 | input | LVR | data | in | no comp --> only transistors --> reduce power
26 | bias | LVR | bias | in
27 | ref | LVR | bias | in
28 | out | LVR | data | out
29 | clk | Clk Gen | logic | in
30 | reset | Clk Gen | logic | in
31 | set | Clk Gen | logic | in
32 | phi1 | Clk Gen | logic | out
33 | phi2 | Clk Gen | logic | out
34 | phir | Clk Gen | logic | out
35 | v_read | WL_mux | bias | in
36 | v_write | WL_mux | bias | in
37 | s0 | WL_mux | logic | in | voltages are analog ---- selectors are from controller (pulses already?)
38 | s1 | WL_mux | logic | in | Last TO: s0,s1,s2 were shared between WL & BL for the decoding
39 | s2 | WL_mux | logic | in
40 | sel | WL_mux | logic | in
41 | out | WL_mux | data | out
42 | vcch_WL | WL_mux | power | in
43 | pad | BL_mux | analog | in/out
44 | BL | BL_mux | data | in
45 | v_erase | BL_mux | bias | in
46 | arch | BL_mux | data | in/out
47 | s0 | BL_mux | logic | in
48 | s1 | BL_mux | logic | in
49 | s2 | BL_mux | logic | in
50 | sel | BL_mux | logic | in
51 | out | BL_mux | data | out
52 | vcch_BL | BL_mux | power | in
53
54
55
56
57
58
59
60
61